## Project Schedule - Gantt Chart
|  |  |  | Action Plan 2022 | [54 empty] | [42]
Coatings
|  |  |  | Project Start: | 2022-07-15
|  |  |  | Display: | Weekly
|  |  |  | Display Period: | 1 | time axis 2022-07-15 to 2023-07-28
[11 empty] | 15 jul '22 | 22 jul '22 | 29 jul '22 | 5 ago '22 | 12 ago '22 | 19 ago '22 | 26 ago '22 | 2 sep '22 | 9 sep '22 | 16 sep '22 | 23 sep '22 | 30 sep '22 | 7 oct '22 | 14 oct '22 | 21 oct '22 | 28 oct '22 | 4 nov '22 | 11 nov '22 | 18 nov '22 | 25 nov '22 | 2 dic '22 | 9 dic '22 | 16 dic '22 | 23 dic '22 | 30 dic '22 | 6 ene '23 | 13 ene '23 | 20 ene '23 | 27 ene '23 | 3 feb '23 | 10 feb '23 | 17 feb '23 | 24 feb '23 | 3 mar '23 | 10 mar '23 | 17 mar '23 | 24 mar '23 | 31 mar '23 | 7 abr '23 | 14 abr '23 | 21 abr '23 | 28 abr '23 | 5 may '23 | 12 may '23 | 19 may '23 | 26 may '23 | 2 jun '23 | 9 jun '23 | 16 jun '23 | 23 jun '23 | 30 jun '23 | 7 jul '23 | 14 jul '23 | 21 jul '23 | 28 jul '23
WBS | Specialty | TASK DESCRIPTION (Actividad) | LEAD | PROGRESS | PLAN START | PLAN END | PLAN DAYS | ACTUAL START | ACTUAL END | ACTUAL DAYS | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54
| Architecture |  | P Gonzalez
| Diagramacion | Diagramas de Zonificacion |  | 0% | 2022-07-15 | 2022-07-18 | 4
|  | Diagramas de Circulacion |  | 0% | 2022-07-18 | 2022-07-18 | 1
|  | Diagramas de Funcionamiento |  | 0% | 2022-07-19 | 2022-07-19 | 1
| Planos | Planta Arquitectonica General |  | 0% | 2022-07-20 | 2022-07-21 | 2
|  | Sembrado de maquinaria, equipos y mesas de trabajo |  | 0% | 2022-07-22 | 2022-07-23 | 2
|  | Áreas administrativas |  | 0% | 2022-07-24 | 2022-07-26 | 3
|  | Áreas de operación |  | 0% | 2022-07-27 | 2022-07-28 | 2
|  | Servicios (areas operartivas) |  | 0% | 2022-08-02 | 2022-08-03 | 2
|  | Servicios (areas administrativas) |  | 0% | 2022-08-04 | 2022-08-05 | 2
|  | Señalizacion Horizontal |  | 0% | 2022-08-08 | 2022-08-09 | 2
|  | Cancelerias |  | 0% | 2022-08-10 | 2022-08-11 | 2
|  | Mobiliario |  | 0% | 2022-08-12 | 2022-08-15 | 4
|  | Instalaciones hidrosanitarios y electricas de servicios basicos |  | 0% | 2022-08-16 | 2022-08-17 | 2
| Proyecto y Obra | Sistema contra incendio |  | 0% | 2022-08-17 | 2022-08-18 | 2
|  | Sistema alarma y dteccion de incendio |  | 0% | 2022-08-15 | 2022-11-04 | 82
| Arquitectura | Boletines complementarios |  | 0% | 2022-07-15 | 2022-11-15 | 124
|  | As Built |  | 0% | 2022-07-15 | 2022-11-15 | 124

## Help
Help
About This Template
This GTM's Gantt Chart Template should be used as formal tool to create a project schedule. You only need to know some basic spreadsheet operations, such as how to insert, delete, copy and paste rows and cells. For more advanced uses, such as defining task dependencies, you will need to know how to enter formulas.
Be sure to read the Getting Started Tips below. If you have any questions regarding how to operate this tool, as well as new suggestions to improve it, do not hesitate to contact PMO/CSI team (information below):
Raphael Mata - PMO/Strategic Initiatives Leader - rrodrigues@gtm.net
Eduardo de Delás - M&A/Strategic Initiatives Manager - edelas@gtm.net
Getting Started Tips
Adding More Rows
When you insert new rows, you should insert a blank row between rows that have the formatting you want. If you do that, the formatting will be copied automatically.
Text Within the Gantt Chart
You can enter text within the gantt chart area, but that text does not move if you adjust the start/end dates or use the scroll bar.
Adding More Columns to the Gantt Chart
If you want to increase the time span shown in chart, you can add columns to the right of the Gantt chart by copying and pasting entire columns.
Conditional Formatting
The bars of the Gantt chart are created using conditional formatting. This spreadsheet is not designed to allow you to change the colors for different bars.
To edit conditional formatting rules, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit all the rules.

## Hoja1
Diagramacion | Diagramas de Zonificacion
Diagramas de Circulacion
Diagramas de Funcionamiento
Planos | Planta Arquitectonica General
Sembrado de maquinaria, equipos y mesas de trabajo
Áreas administrativas
Áreas de operación
Servicios (areas operartivas)
Servicios (areas administrativas)
Señalizacion Horizontal
Cancelerias
Mobiliario
Instalaciones hidrosanitarios y electricas de servicios basicos
| Sistema contra incendio | 3
| Sistema alarma y dteccion de incendio | 3